## 2021 Priorities Overview
Connections for Independent Living | 2021 Operations Plan | % of time
2021 Priorities | 1. Expand and Strengthen the Board of Directors | 13%
| 2. Strengthen CIL financial position through sound financial and business operations/procedures to ensure retention of solid funding sources | 35%
| 3. Retain and strengthen our staff through continuous training and succession planning | 15%
| 4. Develop and implement long-term strategic plan to establish clear priorities and direction | 10%
| 5. Develop and implement a capital improvement plan for facility. | 10%
| 6. Respond to COVID-19 by providing our staff and consumers the support they need | 7%
| 7. Enhance our fundraising capacity through the establishment and implementation of a Development Plan that outlines specific fundraising strategies and related goals for each strategy | 10% | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Staff Lead | Board Liaison | Due | Budget | Risk | Notes
|  |  | October | November | December | January | February | March | April | May | June | July | August | September
1. Board of Directors | OBJECTIVE: Expand and strengthen the board of directors to improve its effectiveness and functionality | 13% | [17 empty] | Board member Josh Fulenwider resigned in March to take the role of Director of Independent Living Services with Connections. Several interviews were conducted. Erica Barraza was chosen and voted onto the Board in Q3. The board matrix has been continuously updated and referenced. The Nominations committee meets regularly.
Tactics | Recruit diverse members who reflect the population we serve |  | X | X |  | X | X | X | X | X | X |  |  |  | RM | BD ACTION |  |  | Avoiding uncomfortable conversations about diversity, equity and inclusion and the intentional recruitment to represent all of the population of our catchment area | New Board member in April 2021. Recruiting is robust and process to recruit, onboard and retain members vastly improved.
| Improve the strength of the board through recruitment of specific subject matter experts and through training |  | X | X |  |  | X | X | X | X | X | X |  |  |  | EM |  |  | Not defining what SME's are needed for this board | Have identified areas of need and intentionally recruiting members with those skills.
| Develop a succession plan for the board | [13 empty] | RM | MJ |  |  | Board members leave unexpectedly and create gaps that put CIL out of compliance with CDLE grant requirements | This was highlighted by Josh Fulenwider leaving the board.
| Develop and implement a consistent on-boarding process for the board |  | X | X | X | X | X | X | [6 empty] | RM | MJ/EM |  |  | Board members who are not prepared and risk loss of engagement with governance of CIL | Development includes a board portal on the website with organized documents. An online training suggestion from Board Source and SOS office. Follow up after each board meeting for new members for the first 6 months.
| Develop and regularly nurture committee's to support the board |  |  |  | X | [9 empty] | RM | BD ACTION |  |  | Committees do not support the progression of operations and governance prioroties identified in Strategic Plan | Finance and Nominating committee's meet regularly through the year. Policies and budget are reviewed prior to recommending to board for action. This has significantly streamlined board work.
2. Finances | OBJECTIVE: Strengthen through sound financial and business operations/procedures to ensure retention of solid funding sources | C
Tactics | Develop and implement solid financial and business practices, including proper budgeting with GAAP |  | X | X | X | X | X | X | X | X | X | X | X | X | RM/JC |  |  |  | Loss of state general funds, federal grants due to noncompliance. Loss of fee for service clientele due to poor invoicing/issues with invoicing properly | Latest audit processs showed all finance systems updated with multiple internal controls. Systems are reconciled and checked regularly. Internal controls are above average due to the use of Childress accounting team. All processes are being tracked monthly to ensure streamlining and mulitple trained individuals to ensure a succession plan.
| Retain all present federal and state funding sources/abide by guidelines of contracts and keep current on all requirements |  | X | X | X | X | X | X | X | X | X | X | X | X | RM/JC/AY |  |  |  | Loss of state general funds, federal grants due to noncompliance. | Reduced to "low risk" in April 2021. Systems are above average
| Secure additional funding through grants and fee-for service programs |  |  |  |  | X |  |  |  |  | X | X | X |  | JF/SA |  |  |  | Not being revenue stream diverse cold weaken program delivery if one revenue source goes away unexpectedly. | FY21 Submitted 8 grants totaling $82,700. To date have received $42,700 in new grant funding (some deliverable in FY22)
| Re-build funding reserves to 6 months of operating expenses |  |  | X |  |  | X |  |  | X |  |  | X |  | RM | Finance Com. |  |  | Inability to operate during any unexpected funding crisis | PPP Loan process assited in income hit during pandemic and allowed Connections to retain staff. Fee for service rate increase being carried out in FY22
| Develop and implement excellent internal audit procedures |  |  | X |  |  | X |  |  | X |  |  | X |  | RM/JC |  |  |  | Loss of funding due to noncompliance during external audit findings | Achieved. Montly A/R and A/P reconciliations, Change Reports for payroll, tracking systems for all are in excellent order.
3. Staff Retention | OBJECTIVE: Provide structured trainings and opportunity for training and develop clear succession planning for all departments | 15%
Tactics | Demonstrate commitment to staff development through training |  | X | X |  |  | X | X |  | X | X |  | X | X | RM/JF/SA | EM |  |  | Poor staff retention and culture | Interpreting: ILS: Harrassment, weekly technology training nowavailable as of3/18/21 | David D. was prvoided a paid training on 4/5/21 and Amber S will be attending a paid training on 5/6/21. Bth classes were provided by Employers Council.
| Retain solid staff leadership |  | X |  |  | X |  |  | X |  |  | X |  |  | RM/JF/SA |  |  |  | Poor staff retention and culture/leadership - threatens org growth | Weekly Leadership meeting, solid conversation and consulting in projects and programs. | Currently developing Amber S as a trainer for ILS as well as grooming to take over management of the SEEKS grant team.
| Ensure we have adequate staffing for all needs and positions |  | X | X |  |  | X |  |  | X |  |  | X |  | RM/JF/SA |  |  |  | Staff resource strain and poor delivery of services to consumers | Developed the Intperperter/IL job description, actively seeking candidates. | Peggy Garcia moved over part-time to IL and still does transitions aprt-time.
| Provide solid human resource service to our staff |  | X | X |  |  |  | X |  |  | X |  |  | X | AY | Mountain States |  |  | Poor staff retention and ability to focus on goals and work priorities | Alloted budget for training, encourage all staff to register for trainings. Have a request and approval process for all trainings and conferences. Staff has regular trainings for tech, safety and HR compliance.
| Develop a succession plan for top leadership | [10 empty] | X | X | X | RM | MJ |  |  | Loss of consistent leadership and organizational function | Widening the bench on leadership team and direct reports
X
4.Long-term Strategy | OBJECTIVE: Develop and implement long-term strategic plan to establish clear priorities and direction | 10%
Tactics | Develop a comprehensive strategic plan |  | X | X |  |  |  | X |  |  | X |  |  | X | RM | BD Action |  |  | Inablity to define direction and allocate resources effecively | Completed in 2020
| Develop a funding plan that allows us to implement our strategic plan |  | X | [8 empty] | X | X | X | RM |  |  |  | Inability to grow funding and allow potential donors to assist with mission
| Add a values statement | [8 empty] | X |  |  | X |  | RR | KH |  |  | Will not effectively communicate with consumers and community at large | Created in Summer, 2021. Added to website in August 2021 along with equity statement.
| Review and evaluate our mission as an organization | [5 empty] | X |  | X | [5 empty] | RR | KH |  |  | Will not effectively communicate with consumers and community at large | New mission statement was created in September 2020 and added to website.
| Consistently monitor our progress toward implementing our strategic plan |  |  |  | X |  |  | X |  |  | X |  |  | X | RM | BD Action |  |  | Plan goals may not move forward or have next logical steps | Reviewed April & October 2021
| Periodically update our strategic plan | [10 empty] | X | X | X | RM | BD Action |  |  | Plan goals may not move forward or have next logical steps | Done October 2021
5. Capital Improvement | OBJECTIVE: Develop and implement a capital improvement plan for our facility | 10%
Tactics | Develop a capital improvement plan for our facility | [5 empty] | X |  |  | X |  |  |  | X | Leadership Team | BD Action |  |  | Outdated facility that does not show the best in accesible workspaces
| Make near-term updates to our building as resources are available |  |  |  |  | X |  |  | X |  |  | X |  |  | RM | BD Action |  |  | Outdated facility that does not show the best in accesible workspaces | Building was purged of old/unusable items, new desks were purchased, interior space was reorganized and painted
| Make larger capital improvements to our building as resources are available |  |  |  |  | X |  |  | X |  |  | X |  |  | RM | BD Action |  |  | Outdated facility that does not show the best in accesible workspaces | WiFi was updatd and new VRI room installed
| Periodically review the available options for moving to a different facility |  |  |  |  | X |  |  | X |  |  | X |  |  | RM | BD Action |  |  | Plan goals may not move forward or have next logical steps to grow CIL | Has not been addressed
6. COVID-19 Response | OBJECTIVE: Respond to COVID-19 by providing our staff and consumers the support they need | 7%
Tactics | Provide COVID 19 support to our consumers/clients |  | X | X | X | X | X | X | X | [5 empty] | RM |  |  |  | Noncompliance with CARES Act grant, underserving disability community and greater isolation issues | Vaccine clinics, info campaigns, web pages, high level info and referral and stakeholder advocacy has been done at all levels and to all ares of our catchment area.
| Respond to the health theat posed by COVID 19 to our staff and consumers |  | X | X | X | X | X | X | X | [5 empty] | RM |  |  |  | Isolation increases and causes mental and physical health issues. Pandemic risks are not mitigated by CIL outreach and communications | Provided grief support for all staff. Focus on mental health support during peer meetings and social media and communicaitons. COVID vaccine was made mandatory for all staff by adopted policy. Workplace 5-start health safety regulations have been achieved.
| Fulfill our CARES Act & All COVID related funding responsibilities |  | X | X | X | X | X | X | X | X | X | X |  |  | RM |  |  |  | Noncompliance will result in funds returned or fines risking the overall financial health and stability of CIL | Completed May 2021.
| Address the long-term impact of the pandemic to our staff and consumers | [8 empty] | X | X | X | X | X | RM | MJ |  |  | Long-term health of those with disabilities on our catchment area/community | Working on hybrid models, increased digital equity and access with Gov. Committee on digital equity. Working with ACCIL on lobbying for additional support. Have received add'l support though ACL
7. Fundraising | OBJECTIVE: Enahance our fundraising capacity through the establishment and implementation of a Development plan that outlines specific revenue stream strategies and related goals for each strategy | 10%
Tactics | Explore consistent revenue streams of fundraising |  |  | X | X |  |  | X |  |  | X |  |  | X | RR | KH |  |  | Not diversifying revenue streams keeps CIL reliant on state and federal grant funding | Created donation page on new website. Participated in Dec 2020 Colorado Gives Day. Robust grant cycle established with 9 grants submitted totalling nearly $87k, 3 being approved to date. Capital campaign through CDBG grant silent phase began Sept. 2021; will be promoted with Dec 7 Colorado Gives Day.
| Fund raise for specific needs (Housing grants, Technology Vouchers, etc.) |  |  | X | X |  |  | X |  |  | X |  |  | X | RR | KH |  |  | Would not allow for sufficient growth in areas that are consumer led needs | Grant applications have been made to benefit specific programs including transitions, housing and capital improvements.
| Establish an endowment | [8 empty] | X |  |  | X |  | RM | Board |  |  | Long-term financial health of CIL is at risk
| Establish a Development plan and team | [10 empty] | X | X |  | RM/DC | KH |  |  | Long-term financial health of CIL is at risk | Grant writing and funding development is in growth phase with increases to education of staff prioritzed.

## Initiatives-Work Plans
Connections for Independent Living | 2021 Operations Plan | 1-2 years | 3-5 years | Staff Lead | Risk | Notes | Notes
Aspirations/Work plans
1. Focus on our core competencies, while working with other agencies to fulfill the unment needs of consumers | OBJECTIVE: To build strong relationships with other municipal services and nonprofits for better access to unmet needs of consumers
| 1. Strengthen current consumer experiences | X |  | JF |  |  | MiCiL overhaul, new online intake portal, making it easier for consumers to sign documents and IL's to update files. Many internal forms were recently updated including the intake form and the closing letter.
| 2. Conduct semi-annual surveys with every consumer to ensure their needs are being met | X |  | JF |  |  | Survey completed summer of 2021. Additional Computer Voucher survey was completed to guide a tech training program that was implemented
| 3. Measure what matters, create metrics in line with priorites and consumer driven programs | X |  | JF/RR |  |  | Using Director Dashboard to track metrics on social media. Recently using GoogleAD grant to target Interpreting dept. and compare to USked reports and mark trends. Created an ILS performance metrics to establish baseline performance for alll ILS team members.
| 4. Provide services within our core competencies while referring our consumers to other agencies to fulfill their other needs | X |  | JF/KT |  |  | Joined the Unite Us online referral program. CIL has an accessible van to provide needed rides and comuter, Connections Cares supplies, (face masks, hand sanitizer, disenfectant,face sheilds,food boxes) to areas that have no public transportation. Established and maintain relationships with local chambers in multiple northeast counties. Hired 1 part time ILS for northeast area of state. Posted additional part time ILS position for other areas of northeast part of state. Expanded suport groups to multiple counties in catchment area. Provide consumers with computers to increase connections and reduce isolation. Outreach presentations to multiple agencies and academic programs in northeast area of state. Completed numerous surveys related to Covid-19 information and needs.
2. Expand Interpreting Services | OBJECTIVE: Be the leader in interpreting services for all of Northern CO and beyond when possible
| 1. Quantify the opportunity to expand interpreting services | X |  | KM |  |  | Expanded through VRI permanent installation, new contracts with RISP, Indpendence Center COSpgs, FEMA
| 2. Develop a systematic plan for the expansion | X |  | KM
| 3. Execute expansion plans with Communications planning | X |  | SA/RR |  |  | SA & RR have met to discuss plans and will meet regularly.
| 4. Monitor and revise the expansion plan |  | X | KM
3. Find new and better ways to connect with consumers through technology | OBJECTIVE: Bridge the digital divide that separates and isolates many people with disabilities
| 1. Assess recent advancements in the use of tech to connect with consumers | X |  | RR/JF |  |  | New tech added: 1) Google Workspace in Dec 2020, 2) Unite Colorado in March 2021, 3) New adaptive-friendly website in Dec 2020.
| 2. Work with consumers to identify additional opportunities to meet their needs through technology | X |  | JF |  |  | Emergency Broadband Benefit is a new program that will expand access to high speed internet
| 3. Build on current communications to provide opportunities to connect people | X |  | RR |  |  | Launched LinkedIn social media in Sept 2020. Relaunched newsletter in print and digital in Sept 2020. Added communications consultant for 3 months beginning March 2020. Including additional staff member for online postings.
| 4. Expand our services through technology to entire catchment area |  | X | RR/KT?JF |  |  | Provide computers to consumers in northeast area of state. Working on developing the Connections Connects program to expand knowledge of and access to the internet. | Support consumers in obtaining cell phones to reduce isolation and improve quality of life.
4. Become the leading Independent Living Center in Colorado | OBJECTIVE: Rise to a shining example of advocacy and consumer led service provisions
| 1. Define what it takes to become the leading IL in Colorado | X |  | Leadership Team |  |  | Core Values Statement written by Leadership Team. Values statement in progress as coordinated by director of communication and amongst all staff.
| 2. Study best-practices nation-wide | X |  | Leadership Team |  |  | Working with Centers for Ind. in CO Springs on desk manuals for all team-members. Attending ILRU tech discussions monthly to particpate in best-practices discussions nationwide. DIL working with program managers across state to update desk manual for that position.
| 3. Innovate on delivering services to consumers/clients |  | X | Leadership Team |  |  | Participation in SEEKS grant has delviered new training to staff that allows us to better serve consumers. Implementation of the VRI room allows us to better serve the DHOH community. Currently developing and implementing a plan to bring technology access and knowledge to consumers in partnership with other area agencies and the EBB.
| 4. Resource and implement a plan for constant improvements |  | X | Leadership Team |  |  | Using Google Calendar staff function to encourage trainings, using committee to inform decision making for things like beneftis and open block hours.
| 5. Monitor progress |  | X | RM |  |  | Implementing All-hands meetings notes, Director Dashboards and cohesive digital communications tools like Dropbox, GDrive, employee portals has increased how we monitor and then can track trends and anomolies.
5. Develop and Implement a Communications plan to rebrand CIL | OBJECTIVE: Increase public awareness of services
| 1. Develop Communications & Markeing plan that incorporates rebranding | X |  | RR |  |  | 2021 plan created in Dec 2020. Needs revision and updating for 2022.
| 2. Increase our exposure to and communications to stakeholders throughout entire catchment area | X |  | RR |  |  | Updated website in Dec 2020. Relaunched newsletter in Sept 2020 (redesigned print & digital Sept 2021). Better, consistent use of social media starting in Sept 2020. New brochure printed April, 2021; reprinted Oct 2021. Launched annual report in July, 2021.
| 3. Create consistent messaging and story-telling | X |  | RR |  |  | Worked with social media consultant to create consistent plan of communication in spring 2021.
| 4. Establish Communications calendar | X |  | RR |  |  | Began calendar in 10/20. Need to revise.
| 5. Fully update website | X |  | RR |  |  | Project begun June 2020; completed Dec 2020 with launch. Site content updating and expanding regularly.
| 6. Execute and adjust plan as conditions change | X | X | RR |  |  | Regularly adjusting communications planning with consultation with RM.
6. Build relationship with community and municipal leaders to expand involvement and advocacy | OBJECTIVE: Increase awareness and advocacy action for the disabled community
| 1. Identify and prioritize community and municipal leaders needed to advocate for the disabled community | X |  | RM/RR |  |  | Joined several Chambers of Commerce in region in 2020. Sending media releases to the Chambers regularly for distribution to member businesses.
| 2. Create intentional, written relationship-building plans for municipal stakeholder | X |  | RM/RR |  |  | Re-designed website, refreshed logo, redesigned marketing materials and launched aggressive public campaign to increase community awareness. This will lead to stronger relationships with key stakeholders throughout service region.
| 3. Identify a menu of appropriate ways that stakeholders can engage with disabled community | X |  | RM/RR |  |  | Annual survey each June, public comment notices at SILC meetings, public awareness thorugh newsletters direct to consumers.
| 4. Begin attending municipal meetings and presenting about CIL services |  | X | RM |  |  | Actively engaged with presentations to Rotary, Kiwanis, Chambers of Commerce, Weld Gives Collaborative.
7. Meet the needs for our services throughout our geographic catchment area | OBJECTIVE: Reach as many people in the disabled community as possible
| 1. Conduct survey's and assessments of unmet needs | X |  | JF/RR |  |  | Survey undertaken for COVID relief in spring 2020, survey for services devloped in 2021 and distributed June 2021. Results aggregated in August and reviewed with staff for input.
| 2. Determine what is within CIL's resources to expand | X |  | Leadership Team |  |  | Covering COVID relief and vaccine plan/awareness is primary task for 2021 and 2022.
| 3. Develop a plan to meet unmet needs in Outreach areas | X |  | JF/KT |  |  | Received another vehichle to allow one to be allocated to northeastern counties. Hired one additional ILS for outreach specific services. Became active with chambers of commerce and service groups in all other 6 counties.
| 4. Acquire one or more mobile service vehicles |  | X | JF/KT |  |  | Completed!
| 5. Open offices or mobile service offices in Outreach areas |  | X | JF/KT |  |  | Mobil vaccine clinic assistance happneing in 2021.